ROLLOUT CHECKLIST

Whiteboard to tablet

A 30-day rollout for your command board

WEEK 1 · SET UP

☐  Pick one champion per shift

☐  Build one template: structure fire

☐  Name divisions and groups as your SOG does

☐  Set PAR to your SOG's interval

☐  Mount and charge tablets in command vehicles

WEEK 2 · TRAIN

☐  20-minute walkthrough on every shift

☐  Every officer takes command once

☐  Practice a PAR from start to All Clear

☐  Practice a Mayday and its close-out

WEEK 3 · DRILL

☐  Run the 60-minute tabletop

☐  Use it at one live training evolution

☐  Debrief: what slowed you down?

WEEK 4 · GO LIVE

☐  Use it on every working fire

☐  Keep the whiteboard as backup

☐  Review the first three activity logs at the officers' meeting

YOU'RE DONE WHEN

☐  Every IC has taken command at least once

☐  Every crew has answered a PAR from its own device

☐  One real incident logged from start to Complete Command

Edit this list to match your SOGs. Add your own dates in the margin.